## Plan
		Total time:		197	258	98	372	298	35
				*R1	R2	R2.5	R3	R4	R5
Model	model interfaces	basic		20
		Packages						15
		Full code	*					20		For all code
	model	in-module		30
		code path				10				Handle code that is spread over several directories
		Beam files						15		See code inside (if present)
		Packages						10
Scan & parse	scanner			6
	parser			20
	link parser to model			10
	comment and string scanner						4
Editing	normal editing	basic		4
		Shortcuts			6
	document model		*			10	20			Editable model
	Code folding				15
Editor utils	syntax highlighting			4
	semantic highlighting						8	8		Records, function definitions, attributes, mm
	edoc highlighting						8
	bracket matching			6
	auto indentation			10						When pressing Enter
	Split editor window				-	-	-			Not available yet in Eclipse
	pretty-printing	fix indentation			6					Just indent nicely, don't split rows (like Emacs)
		Full	*				20			Rearrange text
Templates	Templates	basic		2
	Code snippets					8	8
Navigation	Module Navigator						10
	Go to definition			6	6					R1=only in-module
	call hierarchy (xref)						12
	module outline view			6
	Module dependencies (xref)					4				???
	Open include file				4
Assist	code completion	in-module		10
		full	*		10		20
	popup documentation				15		15			OTP docs; R3 = new format
	documentation view				6
	ext. compilation errors					6	6			Ex: check that called function is exported
	quick fix errors		*				10	20		Many things here
	quick assist		*				10	20		Many things here
Search	search infrastructure					10
	structured compare						16
	search ui					10	10
Refactoring	Core		*					20	30
	UI		*					15	5
Backend	configuring node	code path		6
	distributed backend			6
	support multiple releases			6
	basic console	History, editable		2
	multiple consoles						10
	launching separate node			6
	Connect to existing node						10			Use an existing node as backend
Build	builder	basic		4
		full				10
	cmake builder			8
Debug & tools	debugger interface	Core			20
		UI			20
	debugging aids	Live expressions		10
		auto "print-trace"					10			Automagically set up traces
	profiler							15
	Dialyzer							15
	tracing	Erlang			10		15
		GSN	*#		20		20	20		Requirements?		Lennart Öhman
	GSN tools (Tecsas, GTT, ...)		*#			30	30	20		Quite diffuse – define!		If no time, just menu
Documentation	Help files				15		15
	Design documents
Maintenance	error corrections		**		30		40	40		Could be much more...
	Improve		**		30					Use caches, move more on Erlang side
	support		**		30		30	30		Could be more...
	administration			15	15		15	15